## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Web Scraping
PROJECT ID
PROJECT MANAGER | Jayant G S
DOCUMENT VERSION | 12
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Universities Link |  | 2020-07-06 |  |  | Initail Version | COMPLETED | REVIEWED | Code to genrate region wise links
2 | Scrapper |  | 2020-07-06 |  |  | Added scraping code | COMPLETED | REVIEWED | Code for scrapping region page
3 | Only Enginnering Colleges |  | 2020-07-08 |  |  | Added Code to check enginnering college or not | COMPLETED | REVIEWED | Code to check enginnering college or not
4 | College page link genrator |  | 2020-07-09 |  |  | Added code to genrate college link | COMPLETED | REVIEWED | Code to genrate college link
5 | College Information Scrapping |  | 2020-07-10 |  |  | Added code to scrap college page | COMPLETED | REVIEWED | Code for scrapping college page
6 | Information Extraction |  | 2020-07-10 |  |  | Added Code for Information extraction | COMPLETED | REVIEWED | Code to extract information
8 | Null Check |  | 2020-07-11 |  |  | Added code for null value check | COMPLETED | REVIEWED | null value check
9 | CSV Writer |  | 2020-07-11 |  |  | Added code to genrate csv file | COMPLETED | REVIEWED | Write in csv
10 | CSV Reader |  | 2020-07-13 |  |  | Added csv reader code | COMPLETED | REVIEWED | read csv file for visualization
11 | Added Bar Graph Genration Code |  | 2020-07-13 |  |  | Added Bar graph genration code | COMPLETED | REVIEWED | for why
12 | Added Pi Digram Genration Code |  | 2020-07-13 |  |  | Added Pi plot code | COMPLETED | REVIEWED | for why
13 | Added Discrete Distibution Code |  | 2020-07-16 |  |  | Added Discrete Distribution code | COMPLETED | REVIEWED | for why
14 | Final Code | https://github.com/Ganesh-Rathi/Py_WebScraping | 2020-07-24 |  |  |  | COMPLETED | REVEIWED