## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Web Scraping
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | None
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 |  | Problem statement not undertood properly which lead to confusion for solution and many more problems | Risk | None | Understanding problem statement and clarifying input and output for product | Rolled back to problem statement and got exactly what is needed for project or what is expected to be done | Ganesh Rathi | Closed | None
2 |  | Checking project is feasible or not it may harm planning if feasibility study goes wrong | Feasibility | None | Keep on checking are we going right or not that will help to know is this approach is feasible or not or is this project itself feasible or not | Checked feasibility and changed approach for multiple times | Ganesh Rathi | Closed | None
3 |  | Time management | Resource | Yes | Trying to be ahead of deadlines is necessary else it may lead to failure of project | Worked for more time for some time to cover up pending work | Ganesh Rathi | Closed | None
4 |  | System and hardware | Resource | Yes | Sometimes hardware or software we are using is not compatible for work expected from them so check compatibility before starting work. | System was compatible so no action required | Ganesh Rathi | Closed | None