## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Web Scrapping and Data Visualization of Engineering Colleges.
PROJECT SPONSOR | Cloud Counselage Pvt ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of this project is to develop an automated system for scraping and visualise the details of Engineering Colleges in Maharashtra.
BUSINESS CASE | Cloud Counselage is a Pan India IT, Management, and Career services provider. To expand its reach across all the colleges in Mumbai and surrounding colleges that might be interested to collaborate with the company and automate the application process. The company is expecting interns to develop an automated system for scraping the details of Colleges and contact details of their TPOs .
GOALS/METRICS | To scrap the data from the web, store the details in a file and then perform visualization on that data.
EXPECTED DELIVERABLES | CSV file which contains the college details and visualization using that file.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Importing the data from web, cleaning data and data visualization.
OUTSIDE OF SCOPE | Analysis of data and gathering useful insights.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Ganesh Rathi
SUPPORT RESOURCES | Laptop/PC with Python3 and Python Editor.
SPECIAL NEEDS | Internet for web scrapping details.
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Ganesh Rathi
KEY STAKEHOLDERS | Cloud Counselage, Nierbhey Singh Pahwa and Jayanth GS
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT | To Expand company's reach across all the colleges in Mumbai region that might be interested in collaborating with the company
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Technical Risks :- Poor Quality of Website, resource Website might not contain necessary details. Resource Risks :- As a Intern, I might lack in some aspects of development which will in turn affect the deadline and performance of the project.
ASSUMPTIONS | Many resource websites are available which contains all the necessary details we are looking to scrap from the web.
CONSTRAINTS | Completion of the project within the stringent schedule and strict deadlines.