## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Web Scrapping and Data Visualization of Engineering Colleges.
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-06
PROJECT DELIVERABLE | CSV file which contains the college details and visualization using that file. |  | EXECUTION PHASE END DATE: |  | 2020-07-26
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 31-06-2020
OVERALL PROGRESS
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation
| 1.1 Understand the SDLC life cycle. | 3 | 2020-06-15 | 2020-06-16 | 2 | COMPLETED
| 1.2 Understand the problem statement | 2 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
| 1.3 Study the project methodology. | 4 | 2020-06-18 | 2020-06-20 | 3 | COMPLETED
2. Planning
| 2.1 Complete Project Charter | 4 | 2020-06-22 | 2020-06-23 | 2 | COMPLETED
| 2.2 Complete SRS document | 2 | 2020-06-24 | 2020-06-24 | 1 | COMPLETED
| 2.3 Design model | 5 | 2020-06-25 | 2020-06-27 | 3 | COMPLETED
| 2.4 Project Plan | 7 | 2020-06-29 | 2020-06-02 | 4 | COMPLETED
3. Execution
| 3.1 Update RAID log |  | 2020-07-06 | 2020-07-26 |  | COMPLETED
| 3.2 Update Development log |  | 2020-07-06 | 2020-07-26 |  | COMPLETED
| 3.3 Gathering necessary URLs. | 3 | 2020-07-06 | 2020-07-08 | 3 | COMPLETED
| 3.4 Scrapping required details. | 12 | 2020-07-09 | 2020-07-14 | 6 | COMPLETED
| 3.5 Cleaning the data. | 4 | 2020-07-15 | 2020-07-17 | 3 | COMPLETED
| 3.6 Storing the data in CSV file. | 4 | 2020-07-18 | 2020-07-20 | 3 | COMPLETED
| 3.7 Visualizing the data. | 8 | 2020-07-21 | 2020-07-25 | 5 | COMPLETED
4. Testing/Debugging
| 4.1 Debugging the source code for any exceptions. | 3 | 2020-07-27 | 2020-07-28 | 2 | COMPLETED
| 4.2 Verifying and validating the output with the desired output. | 1 | 2020-07-29 | 2020-07-29 | 1 | COMPLETED