## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0
| Project title: | Web Scraping |  | Project Id: | Live Project | Project Manager: | Jayant G S |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-25 | Project Team Lead: | Ganesh Rathi |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 6 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Source Site Down | Impact project shedule and delivary | Alternative site | Ganesh Rathi | Moderate |  | Closed | Risk
2 | Assumption | No Authentication needed |  |  | Ganesh Rathi | Moderate |  | Closed | Assumption
3 | Dependency | Internet Connection | Impact on project shedule and delivary | Use stable internet | Ganesh Rathi | Low |  | Closed | Issue
4 | Risk | Failure to follow methodology | Difficulty to keep track with shedule | Follow the methodology | Ganesh Rathi | Low | 2 | Closed | Dependency
5 | Dependency | Visualization depends on csv | Unable to visualize data | Genrate CSV | Ganesh Rathi | Low |  | Closed
6 | Issue | Code Integration | Final Project Delivary |  | Ganesh Rathi | High |  | Closed | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24